## Sheet1
PROJECT TIMELINE
PROJECT TITLE : SALES INVENTORY MANAGEMEMT FOR RAI ELECTRICAL SUPPLY AND GENERAL MERCHANDIZE | CLIENT INFORMATION AND BILLING SYSTEM FOR LIZLY SKINCARE AND WELLNESS CLINIC
Task Name: | Task Description | Status | Assigned to | Start Date | End date | Start on day | Duration days
Login page | Admin can login | on process | Jaso | 2025-03-04 | 04/25/2025 | 3 | 22 days
Admin Dashboard | Admin can navigate dashboard | on process | Jaso | 2025-03-04 | 04/25/2025 | 3 | 22 days
All Services | Admin can manage the all services page | done | Jaso | 2025-03-04 | 04/25/2025 | 3 | 22 days
Memberships | Admin manages the membership details also can add member | done | Labadan | 2025-03-04 | 04/25/2025 | 3 | 22 days
Membership Reports | Admin can manage and monitor the memberships | done | Sulib | 2025-03-04 | 04/25/2025 | 3 | 22 days
Beauty Deals | Admin can manage the promos and discount | on process | Sulib | 2025-03-04 | 04/25/2025 | 3 | 22 days
Service Acquire | Admin can handle the service acquire of customers | done | Sulib | 2025-03-04 | 04/25/2025 | 3 | 22 days
Reports | Admin can generate reports for return | done | Sulib | 2025-03-04 | 04/25/2025 | 3 | 22 days
MILESTONE 1
Customers Page | Admin can manage the customers details | done | Labadan | 04/292025 | 05-13-2025 | 29 | 15 days
Invoice Page | Admin can manage the invoices of customers | done | Jaso | 04/29/2025 | 05-13-2025 | 29 | 15 days
Login page | Receptionist can login | on process | Labadan | 04/29/2025 | 05-13-2025 | 29 | 15 days
MILESTONE 2
Receptionist Dashboard | Receptionist can navigate dashboard | on process | Jaso | 05-16-2025 | 05-31-2025 | 16 | 16 days
All Services | Receptionist can view only the services | done | Jaso | 05-16-2025 | 05-31-2025 | 16 | 16 days
Memberships | Receptionist can monitor the memberships | done | Jaso | 05-16-2025 | 05-31-2025 | 16 | 16 days
Beauty Deals | Receptionist can monitor the promos and discounts | on process | Jaso | 05-16-2025 | 05-31-2025 | 16 | 16 days
Service Acquire | Receptionist handles the customer service acquire | done | Jaso | 05-16-2025 | 05-31-2025 | 16 | 16 days
Customers Page | Receptionist can monitor the customers information | done | Jaso | 05-16-2025 | 05-31-2025 | 16 | 16 days
Invoice Page | Receptionist can monitor the invoices of customers | done | Jaso | 05-16-2025 | 05-31-2025 | 16 | 16 days
MILESTONE 3
Login page | Admin can login | done | Jaso | 2025-07-07 | 07/25/2025 | 7 | 17 days
Admin Dashboard | Admin can navigate dashboard | done | Jaso | 2025-07-07 | 04/25/2025 | 7 | 17 days
All Services | Admin can manage the all services page | done | Jaso | 2025-07-07 | 04/25/2025 | 7 | 17 days
Memberships | Admin manages the membership details also can add member | done | Jaso | 2025-07-07 | 04/25/2025 | 7 | 17 days
Membership Reports | Admin can manage and monitor the memberships | done | Jaso | 2025-07-07 | 04/25/2025 | 7 | 17 days
Beauty Deals | Admin can manage the promos and discount | on process | Jaso | 2025-07-07 | 04/25/2025 | 7 | 17 days
Service Acquire | Admin can handle the service acquire of customers | done | Jaso | 2025-07-07 | 04/25/2025 | 7 | 17 days
Reports | Admin can generate reports for return | done | Jaso | 2025-07-07 | 04/25/2025 | 7 | 17 days